## Introduction
Aether Flow
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Aether Flow
| Organizations | CS492 Team Project
| Project | AetherFlow
| UI/UX Specialist & Lead | Daniel Rhoads
| Scrum Master (Project Coordinator) | Alex Johnston
| Logic Architect (Backend) | Nathan Nied
| Detail-Oriented Tester (QA) | Garrett Lassalle
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
AF-101 | Secure User Login | As a Warehouse Manager, I want to login with encrypted credentials so that only authorized personnel can access the inventory. | Password hashing implemented; HTTPS encryption active; System blocks unauthorized login attempts. | 1 | 1 | Nathan Nied
AF-102 | Cloud Repository & Version Control | As a Developer, I want a centralized cloud repository so that the team can collaborate concurrently and maintain version control. | GitHub repo initialized; Standard folder structure; Vercel/Hosting connected for deployment. | 1 | 1 | Alex Johnston
AF-103 | Real-Time Inventory Search by SKU/Name | As a Staff Member, I want to search items by SKU or Name so I can verify stock levels in real-time. | Results return in < 2 seconds; Search supports partial SKU matching; Filters by category. | 2 | 1 | Nathan Nied
AF-104 | Stock Adjustment Audit Log | As an Administrator, I want to see a log of all stock adjustments so that we have an operational record of changes. | Log entries include User ID and Timestamp; Data is stored in a read-only format for non-admins. | 2 | 1 | Nathan Nied
AF-105 | Low-Stock Visual Alert | As a Manager, I want a visual warning when stock is below 10 units so I know when to reorder goods. | UI turns Alert Crimson (#D50000) for low stock; Alert triggers automatically upon quantity change. | 2 | 2 | Daniel Rhoades
AF-106 | Add New Item to Inventory Catalog | As a Staff Member, I want to add new items to the catalog so the inventory reflects current warehouse holdings. | New SKUs saved to SQL database; Data validation ensures ISBN/SKU format is correct. | 3 | 2 | Nathan Nied & Garrett Lassalle

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | AetherFlow
|  | Sprint # |  | 1
|  | Start date |  | 2026-05-05
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18
T101 | AF-102 | Create GitHub Repo & Invite Team | Daniel | 2 | 2026-05-05: 1; 2026-05-07: 2; 2026-05-12: 3; 2026-05-15: 3
T102 | AF-101 | Design Encrypted SQL User Tables | Nathan | 6 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 1 | 1 | 2
T103 | AF-101 | Code Login Screen UI (Aether Blue) | Daniel | 5 | 2026-05-06: 3; 2026-05-07: 2; 2026-05-13: 2
T104 | AF-101 | Implement JWT/Password Hashing | Nathan | 5 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
T105 | AF-104 | Map User Stories to Personas | Jesus | 4
T106 | AF-106 | Draft Security Test Plan for login system | Garrett | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
T107 | AF-101 | Initialize Kanban/Sprint Board | Alex | 6 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1
T108 | AF-101 | Test invalid login handeling | Garrett | 2 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 2
T109 | AF-101 | Verify password validation requirements | Garrett | 2 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 2
T110 | AF-102 | Review ISBN/SKU validation requiremnts | Garrett | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T111 | AF-102 | Test duplicate SKU rejection handeling | Garrett | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T112 | AF-101 | Verify role-based access permissions | Garrett | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T113 | AF-101 | Document bugs and validation results | Garrett | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
|  | Remaining units (actual) |  | 42 | 37 | 26 | 15 | 7 | -1 | -6 | -10 | -18 | -27 | -33 | -41 | -47 | -57 | #N/A
|  | Remaining units (ideal) |  |  | 39 | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
[10 empty] | 0 | 34 | [5 empty] | 0
[10 empty] | 10 | 0 | [5 empty] | 10

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | AetherFlow
|  | Sprint # |  | 2
|  | Start date |  | 2026-05-19
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01
AF-201 | AF-100 | Restructure local React/Vite development layers to support absolute path mapping schemas (@/*) via vite.config.js and jsconfig.json. Configure framework settings to target and scale components within a WSL local environment. | Daniel Rhoads | 3 | 2026-05-20: 3
AF-202 | AF-100 | Resolve compilation block where Vite server bypassed global stylesheets. Install core CSS compilers, initialize configuration files via npx tailwindcss init -p, and optimize the content array to prevent infinite loops in background folders. | Daniel Rhoads | 4 | 2026-05-20: 5
AF-203 | AF-100 | Build out the visual user interface layer by linking global styling rules directly to the React application mount point (src/main.jsx). Enforce strict 8px layout border-radius guidelines (0.5rem). Map custom theme tokens. | Daniel Rhoads | 3 | 2026-05-19: 2.5
AF-204 | AF-103 | Implement input string handling logic on the primary dashboard interface. Integrate non-blocking frontend filtering routines that instantly parse structural descriptions and asset labels against live alphanumeric keystrokes. | Daniel Rhoads | 3 | 2026-05-19: 2
AF-205 | AF-105 | Develop custom conditional evaluation elements across dataset rows to isolate low-velocity inventory assets. Quantities sinking to or below 10 remaining units must dynamically override default layouts to trigger an active visual status flag. | Daniel Rhoads | 4
AF-206 | AF-206 | Resolve remote head mismatch block by executing Git rebasing structures. Fix code merge conflicts in the workspace authentication file tree manually, finalize local commits, and push them to launch an error-free production deploy via Vercel. | Daniel Rhoads | 3
AF-207 | Admin | Contacted and followed up with the Student Advisor regarding the administrative grading incident and output verification. | Daniel Rhoads | 1.5 | 2026-05-22: 1.5
AF-208 | Admin | Git source tree maintenance, WSL directory configuration, and project file alignment. | Daniel Rhoads | 2 | 2026-05-22: 2
AF-209 | Admin | Weekly Group Scrum Meeting and coordination. | Daniel Rhoads | 1 | bar: 2026-05-22
AF-210 | AF-101 | Test invalid login and authentication edge cases | Garrett Lassalle | 2 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-211 | AF-101 | Verify minimum password length enforcement | Garrett Lassalle | 2 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-212 | AF-101 | Test script injection and invalid character handling | Garrett Lassalle | 2 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-213 | AF-101 | Verify localhost integration testing environment | Garrett Lassalle | 1 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-214 | AF-101 | Perform mobile viewport responsiveness testing | Garrett Lassalle | 2 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-215 | AF-101 | Test user registration input validation | Garrett Lassalle | 1 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-216 | AF-101 | Verify automated test timing/delays to avoid Vercel WAF blocking | Garrett Lassalle | 1 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-217 | AF-101 | Test login and registration API input safety | Garrett Lassalle | 2 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.25; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-218 | AF-103 | Review ISBN/SKU validation requirements | Garrett Lassalle | 1 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.5; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-219 | AF-103 | Prepare inventory SKU/search validation test cases | Garrett Lassalle | 1 | 2026-05-19: 0.25; 2026-05-20: 0; 2026-05-21: 0.5; 2026-05-22: 0; 2026-05-23: 0.5; 2026-05-24: 0.25
AF-220 | AF-101 | Document Sprint 2 QA validation results in /docs | Garrett Lassalle | 2 | 2026-05-19: 1; 2026-05-20: 0; 2026-05-21: 0.5; 2026-05-22: 0; 2026-05-23: 2; 2026-05-24: 1
|  | Remaining units (actual) |  | 80 | 72 | 64 | 60.5 | 56 | 49 | 45.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 74.2857 | 68.5714 | 62.8571 | 57.1429 | 51.4286 | 45.7143 | 40 | 34.2857 | 28.5714 | 22.8571 | 17.1429 | 11.4286 | 5.7143 | 0
[10 empty] | 0 | 24.5 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0