## Introduction
AetherFlow Project Portal
Project Name: | AetherFlow: Cloud-Native Inventory Management
Project Summary: | A cloud-native IMS designed for supply chain visibility and automated stock alerts

## Product Backlog
Project: AetherFlow
UI\UX Specialist & Lead: Daniel Rhoads
Logic Architect (Backend): Alex Johnston
Detail-Oriented Tester (QA): Garrett Lassalle
Business Analyst (Documentation Lead): Jesus Salas
Scrum Master (Project Coordinator): Nathan Nied
Story ID | Description | Acceptance Criteria | Priority
AF-101 | As a Warehouse Manager, I want to login with encrypted credentials so that only authorized personnel can access the inventory. | Password hashing implemented; HTTPS encryption active; System blocks unauthorized login attempts. | 1
AF-102 | As a Developer, I want a centralized cloud repository so that the team can collaborate concurrently and maintain version control. | GitHub repo initialized; Standard folder structure; Vercel/Hosting connected for deployment. | 1
AF-103 | As a Staff Member, I want to search items by SKU or Name so I can verify stock levels in real-time. | Results return in < 2 seconds; Search supports partial SKU matching; Filters by category. | 2
AF-104 | As an Administrator, I want to see a log of all stock adjustments so that we have an operational record of changes. | Log entries include User ID and Timestamp; Data is stored in a read-only format for non-admins. | 2
AF-105 | As a Manager, I want a visual warning when stock is below 10 units so I know when to reorder goods. | UI turns Alert Crimson (#D50000) for low stock; Alert triggers automatically upon quantity change. | 2
AF-106 | As a Staff Member, I want to add new items to the catalog so the inventory reflects current warehouse holdings. | New SKUs saved to SQL database; Data validation ensures ISBN/SKU format is correct. | 3

## Sprint 1
Project: AetherFlow: Cloud-Native Inventory Management
Sprint #: 1
Start Date: | 2026-05-05
End Date: | 2026-05-12
Total Team Members: 5
Sprint Goal: Establish core infrastructure, secure authentication, and the initial SQL database schema.
Task ID | Story ID | Description | Responsibility | Initial Estimate | Total Actual | Day 1- Day 10 | Status
T-101 | AF-102 | Create GitHub Repo & Invite Team | Daniel | 2
T-102 | AF-101 | Design Encrypted SQL User Tables | Alex | 6
T-103 | AF-101 | Code Login Screen UI (Aether Blue) | Daniel | 5
T-104 | AF-101 | Implement JWT/Password Hashing | Alex | 5
T-105 | AF-104 | Map User Stories to Personas | Jesus | 4
T-106 | AF-101 | Draft Security Test Plan for login system | Garrett | 2 | 1
T-107 | AF-101 | Initialize Kanban/Sprint Board | Nathan | 6
T-108 | AF-101 | Test invalid login handeling | Garrett | 2 | 2
T-109 | AF-101 | Verify password validation requirements | Garrett | 2 | 2
T-110 | AF-102 | Review ISBN/SKU validation requiremnts | Garrett | 3 | 2
T-111 | AF-102 | Test duplicate SKU rejection handeling | Garrett | 2 | 2
T-112 | AF-101 | Verify role-based access permissions | Garrett | 2 | 2
T-113 | AF-101 | Document bugs and validation results | Garrett | 1 | 1