## Introduction
Airline Reservation System
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Airline Reservation System
| Organizations | CS492 Team Project
| Project | AetherFlow
| UI/UX Specialist & Lead | Daniel Rhoades
| Scrum Master (Project Coordinator) | Alex Johnston
| Logic Architect (Backend) | Nathan Nied
| Detail-Oriented Tester (QA) | Garrett Lassalle
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
AF-101 | Secure User Login | As a Warehouse Manager, I want to login with encrypted credentials so that only authorized personnel can access the inventory. | Password hashing implemented; HTTPS encryption active; System blocks unauthorized login attempts. | 1 | 1 | Nathan Nied
AF-102 | Cloud Repository & Version Control | As a Developer, I want a centralized cloud repository so that the team can collaborate concurrently and maintain version control. | GitHub repo initialized; Standard folder structure; Vercel/Hosting connected for deployment. | 1 | 1 | Alex Johnston
AF-103 | Real-Time Inventory Search by SKU/Name | As a Staff Member, I want to search items by SKU or Name so I can verify stock levels in real-time. | Results return in < 2 seconds; Search supports partial SKU matching; Filters by category. | 2 | 1 | Nathan Nied
AF-104 | Stock Adjustment Audit Log | As an Administrator, I want to see a log of all stock adjustments so that we have an operational record of changes. | Log entries include User ID and Timestamp; Data is stored in a read-only format for non-admins. | 2 | 1 | Nathan Nied
AF-105 | Low-Stock Visual Alert | As a Manager, I want a visual warning when stock is below 10 units so I know when to reorder goods. | UI turns Alert Crimson (#D50000) for low stock; Alert triggers automatically upon quantity change. | 2 | 2 | Daniel Rhoades
AF-106 | Add New Item to Inventory Catalog | As a Staff Member, I want to add new items to the catalog so the inventory reflects current warehouse holdings. | New SKUs saved to SQL database; Data validation ensures ISBN/SKU format is correct. | 3 | 2 | Nathan Nied & Garrett Lassalle

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | AetherFlow
|  | Sprint # |  | 1
|  | Start date |  | 2026-05-05
|  |  | Total Team Members | 5
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18
T101 | AF-102 | Create GitHub Repo & Invite Team | Daniel | 2
T102 | AF-101 | Design Encrypted SQL User Tables | Nathan | 6 | 2026-05-05: 1; 2026-05-06: 2; 2026-05-07: 1; 2026-05-08: 1; 2026-05-09: 2; 2026-05-10: 1
T103 | AF-101 | Code Login Screen UI (Aether Blue) | Daniel | 5
T104 | AF-101 | Implement JWT/Password Hashing | Nathan | 5 | 2026-05-05: 0; 2026-05-06: 1; 2026-05-07: 1; 2026-05-08: 2; 2026-05-09: 1; 2026-05-10: 1
T105 | AF-104 | Map User Stories to Personas | Jesus | 4
T106 | AF-106 | Draft Security Test Plan for login system | Garrett | 2
T107 | AF-101 | Initialize Kanban/Sprint Board | Nathan | 6 | 2026-05-05: 1; 2026-05-06: 2; 2026-05-07: 2; 2026-05-08: 1; 2026-05-09: 1; 2026-05-10: 1
T108 | AF-101 | Test invalid login handeling | Garrett | 2
T109 | AF-101 | Verify password validation requirements | Garrett | 2
T110 | AF-102 | Review ISBN/SKU validation requiremnts | Garrett | 3
T111 | AF-102 | Test duplicate SKU rejection handeling | Garrett | 2
T112 | AF-101 | Verify role-based access permissions | Garrett | 2
T113 | AF-101 | Document bugs and validation results | Garrett | 1
|  | Remaining units (actual) |  | 42 | 40 | 35 | 31 | 27 | 23 | 20 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 39 | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
[10 empty] | 0 | 34 | [5 empty] | 0
[10 empty] | 10 | 0 | [5 empty] | 10

## Sprint 2
Sprint #2Tracking Sheet
Project
|  | Sprint # |  | 2
Start date
|  |  | Total Team Members | TBD
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12
|  | Remaining units (actual) |  | #VALUE! | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[10 empty] | 0 | 0 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0